## Sheet1
PuMpUp Project Cost Estimate
Prepared by: Ankit Prakash | Date: | 2019-05-24
| Units/Hrs. | Cost/Unit/Hrs. | Subtotals | WBS Level 2 totals | % of totals
WBS Items
1.Sketching |  |  |  | 7910 | 14.13%
1.1 Project Manager | 25 | 70 | 1750
1.2 Team Lead | 56 | 60 | 3360
1.3 UI Designer and UI Developer | 56 | 50 | 2800
2.Sample Data |  |  |  | 2000 | 3.573%
2.1 Developer | 40 | 50 | 2000
3.Architecture |  |  |  | 12100 | 21.61%
3.1 Project Manager | 100 | 70 | 7000
3.2 MVP Tools | 1 | 100 | 100
3.3 MVP Developer | 100 | 50 | 5000
4.Development |  |  |  | 14520 | 25.94%
4.1 MS Office licenses | 2 | 20 | 40
4.2 Project Manager | 50 | 70 | 3500
4.3 Team Lead | 100 | 60 | 6000
4.4 Developer | 100 | 50 | 5000
4.5 Project management tools | 1 | 20 | 20
5.Testing |  |  |  | 19450 | 34.74%
5.1 Test Manager | 50 | 70 | 3500
5.2 Test Lead | 145 | 60 | 8700
5.3 Project Team members | 145 | 50 | 7250
Total Project Cost Estimates |  |  |  | 55980 | 100%