## Sheet1
PuMpUp Project Cost Estimate
Prepared by: Ankit Prakash | Date: | 2019-05-24
| Units/Hrs. | Cost/Unit/Hrs. | Subtotals | WBS Level 2 totals | % of totals
WBS Items
1.Sketching |  |  |  | 3800 | 13.89%
1.1 Project Manager | 25 | 40 | 1000
1.2 Team Lead | 56 | 30 | 1680
1.3 UI Designer and UI Developer | 56 | 20 | 1120
2.Sample Data |  |  |  | 1200 | 4.386%
2.1 Developer | 40 | 30 | 1200
3.Architecture |  |  |  | 6100 | 22.3%
3.1 Project Manager | 100 | 40 | 4000
3.2 MVP Tools | 1 | 100 | 100
3.3 MVP Developer | 100 | 20 | 2000
4.Development |  |  |  | 7010 | 25.62%
4.1 MS Office licenses | 2 | 20 | 40
4.2 Project Manager | 50 | 40 | 2000
4.3 Team Lead | 100 | 30 | 3000
4.4 Developer | 100 | 20 | 2000
4.5 Project management tools | 1 | 10 | 10
5.Testing |  |  |  | 9250 | 33.81%
5.1 Test Manager | 50 | 40 | 2000
5.2 Test Lead | 145 | 30 | 4350
5.3 Project Team members | 145 | 20 | 2900
Total Project Cost Estimates |  |  |  | 27360 | 100%